## Sprint Calculator
SPRINT PREDICTABILITY CALCULATOR
Purpose: estimate predictable sprint velocity by comparing historical velocity with current sprint team capacity after deductions.
1. SPRINT INPUTS
Sprint Start Date | 2026-10-01 | Sprint End Date | 2026-10-14
Sprint Working Days | 10 | Calculation | Mon–Fri working days
2. CURRENT SPRINT TEAM CAPACITY — ENTER YELLOW CELLS
Person Name | Location | Allocated Days | Public Holiday | Planned Leave | Out-of-Sprint Events | Other Deductions | Actual Working Days | Deduction % | Notes
Person 1 | Pune | 10 | 1 | 0 | 0 | 0 | 9 | 10%
Person 2 | Pune | 10 | 1 | 0 | 0 | 0 | 9 | 10%
Person 3 | Pune | 10 | 1 | 0 | 0 | 0 | 9 | 10%
Person 4 | Pune | 10 | 1 | 0 | 0 | 0 | 9 | 10%
Person 5 | Zurich | 10 | 1 | 0 | 0 | 0 | 9 | 10%
Person 6 | Zurich | 10 | 2 | 0 | 0 | 0 | 8 | 20%
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
TEAM TOTAL |  | 60 | 7 | 0 | 0 | 0 | 53 | 11.67%
3. CAPACITY SUMMARY — ALLOCATED vs AVAILABLE TEAM
Allocated Working Days |  | Headcount Allocated |  | Actual Working Days |  | Headcount Available |  | Capacity Loss
60 |  | 6 |  | 53 |  | 5.3 |  | 11.67%
Headcount Allocated = Allocated Working Days ÷ Sprint Working Days ¦ Headcount Available = Actual Working Days ÷ Sprint Working Days
4. HISTORICAL VELOCITY INPUTS & PREDICTION
N-2 Sprint | N-1 Sprint | N Sprint |  | Velocity Calculation | Velocity Calculation |  | PREDICTABLE VELOCITY | PREDICTABLE VELOCITY | PREDICTABLE VELOCITY
45 | 50 | 55 |  | Average Velocity | 50 |  | Average Velocity × (Headcount Available ÷ Headcount Allocated)
|  |  |  | Headcount Allocated | 6
|  |  |  | Headcount Available | 5.3 |  | 44.1667
|  |  |  | Capacity Factor | 0.88333
Model logic: predictable velocity scales the 3-sprint average by the ratio of available team capacity to allocated team capacity.
COLOUR LEGEND
Yellow | Manual input |  | Green | Calculated result |  | Blue | Section / guidance |  | Gray = explanation
Enter or update these cells |  |  | Do not edit formulas |  |  | Section headings |  |  | Formula / notes